## Sheet1
upload_mode | upload_level | project_number | FX_Language | Currency | Contract_Total | parent_task | task | unit_of_measure | invoicing_instruction | units | unit_cost | achieved_units
NEW | HEADER | 350215 | No | USD | 1788000
NEW | LINE | 350215 | No | USD | 1788000 | REGULATORY (R) | R1. Preparation & Compilation of CTA Core Dossier | Study |  | 1 | 365000 | 1
NEW | LINE | 350215 | No | USD | 1788000 | REGULATORY (R) | R2. CTA Ongoing Maintenance | CTA Submission / Update |  | 200 | 5860.68 | 50
NEW | LINE | 350215 | No | USD | 1788000 | REGULATORY (R) | R12. Regulatory Consulting | Month |  | 20 | 12000 | 10
NEW | LINE | 350215 | No | USD | 1788000 | REGULATORY (R) | R13. Regulatory Meetings (telecon) | Teleconference |  | 30 | 240 | 10
NEW | LINE | 350215 | No | USD | 1788000 | REGULATORY (R) | R14. Regulatory Meetings (telecon) | Teleconference |  | 100 | 28 | 50
NEW | LINE | 350215 | No | USD | 1788000 | PRE-STUDY ACTIVITIES (PS) | PS1. Protocol/Protocol Amendment(s) Review | Protocol Review |  | 1 | 3444 | 1
NEW | LINE | 350215 | No | USD | 1788000 | PRE-STUDY ACTIVITIES (PS) | PS14d. Competent Authority Submissions | CA Submission |  | 3 | 4658.9 | 3
NEW | LINE | 350215 | No | USD | 1788000 | PRE-STUDY ACTIVITIES (PS) | PS14f. Substantial Protocol Amendment Plan Development & Coordination | Amendment |  | 4 | 9948.78 | 4
NEW | LINE | 350215 | No | USD | 1788000 | PRE-STUDY ACTIVITIES (PS) | PS14j. Substantial Protocol Amendment Competent Authority Submissions | Submission |  | 4 | 3289.95 | 4
NEW | LINE | 350215 | No | USD | 1788000 | PRE-STUDY ACTIVITIES (PS) | PS15. Trial Master File/eTMF Set-up | Study |  | 1 | 9500 | 1
NEW | LINE | 350215 | No | USD | 1788000 | PRE-STUDY ACTIVITIES (PS) | PS16. Trial Master File Maintenance | Month |  | 45.7947 | 1193.43 | 25.79
NEW | LINE | 350215 | No | USD | 1788000 | PRE-STUDY ACTIVITIES (PS) | PS17. Investigator Agreements/Contracts | Site |  | 8 | 2084.94 | 4
NEW | LINE | 350215 | No | USD | 1788000 | PRE-STUDY ACTIVITIES (PS) | PS18. Investigator Agreements/Contracts Amendments | Site*Update |  | 20 | 550 | 10
NEW | LINE | 350215 | No | USD | 1788000 | PRE-STUDY ACTIVITIES (PS) | PS19. Investigator Grant Negotiation | Site |  | 8 | 1578.34 | 8
NEW | LINE | 350215 | No | USD | 1788000 | PRE-STUDY ACTIVITIES (PS) | PS20. Investigator Grant Negotiation Amendments | Site |  | 20 | 776.6 | 10
NEW | LINE | 350215 | No | USD | 1788000 | PRE-STUDY ACTIVITIES (PS) | PS21. Investigator Grants; Payment Administration/Tracking & Actual Payments | Payment / Batch |  | 355 | 300.12 | 55
NEW | LINE | 350215 | No | USD | 1788000 | PRE-STUDY ACTIVITIES (PS) | PS23. Investigator Meeting - Materials Development | Study |  | 1 | 2737 | 1
NEW | LINE | 350215 | No | USD | 1788000 | PRE-STUDY ACTIVITIES (PS) | PS24. Investigator Meeting - Attend/Participate | Investigator Meeting |  | 2 | 8800 | 2
NEW | LINE | 350215 | No | USD | 1788000 | PRE-STUDY ACTIVITIES (PS) | PS25. Other Direct (Kick-off Meeting) | Meeting |  | 1 | 3607.55 | 1
NEW | LINE | 350215 | No | USD | 1788000 | PRE-STUDY ACTIVITIES (PS) | PS27. Other Direct (Support of Urgent Safety Measures Activities) | CA Submission |  | 1 | 6506.29 | 1